## Slide 1: DECA Project Final Report 2018 Athens 7-9 Nov.2018
B.6. Quality control during project implementation
Relator : SPARTACO GRIECO – MSV Basket

## Slide 2: DECA Diagram Consortium

## Slide 3: Quality Control - Project Implementation
Project Framework
Sport Implementation Evaluation
Risk Mitigation Plan
Result Quality Management
Organization Timeline Meetings
Validation & Meeting Analysis
NOTE:
To change images on this slide, select a picture and delete it. Then click the Insert Picture icon
in the placeholder to insert your own image.

## Slide 4: Project Framework
- Teamwork in specific groups according to the different roles in the project.
- Individual presentation of the work developed by each partner, and consolidation of the information gathered by the PMO.
- Review of the project progress and analysis of contingencies.
- Production of a meeting minute by the host Organization.
- continuous communication among partners
- maintaining periodical conference skype call meetings
- 4 Periodical project reports
- Official reports for EU
- preparation of both technical and financial reports
Communication
Project Monitoring
Project Reporting

## Slide 5: Sport Implementation Evaluation
First Evaluation Visit
Bremen / Bremehaven / Cuxhaven
9/13 February 2017
Second Evaluation Visit
Virtual Meeting + Survey
September / October 2018
DECA Report Progression
First report
Second report
Final Evaluation Report

## Slide 6: DECA RISK MITIGATION PLAN
RISK | MITIGATION
Project Team members changes | Reserve list of potential replacement people
Activities delay | Alternative plan of activities.
Unexpected expenses | Grant review and exchange of amounts between different chapters of the approved grant.
Employers firing players | Intermediation by PractiGO SL. Meeting between Local Project Manager, Players, Employers and PractiGO SL representative.
Players withdrawal / leaving the project | Revision of commitment letter.
Project partner organizations conflicts | Notification to Project Coordinator, acting as judge, supported by International Project Manager.
Sport injures | Medical revision of the affected player. Review of potential pathways: Light injure continuity in the project. Severe injure leaving the project, return to origin country.

## Slide 7: Result Quality Management
The description of the 2°evaluation was done according to the following elements:
- evaluation of questionnaires with personal opinions;
- interview voice recording individually
- second Evaluation Visit - done on October 2018

## Slide 8: Diagram of DECA’s Quality Management
TOPICS | INTERVIEWED | PARTNERS
Evaluation Sport Tutor 2017-2018 | Nils Ruttmann | Eisbären Bremerhaven
VET provider/ language course 2017-2018 | Oliver Schneider 2017-2018 Kerstin Hollwedel 2017 | PractiGo
Evaluation Companies | Klaus Kentsch 2017 Steffen Heumann 2018 | Haeven Hostel PIER 6
DECA Management | Uli Mix 2017 2018 | Minister of Interior
Evaluation Students/ athletes | Klavs Krastins(2017-2018) Arnau Triginer(2017-2018) Aleix Pujadas(2017) Alberto Artiles Aguilar(2017) | Athletes Eisbaren Athletes Cuxhaven
Partners Sport Clubs | Jane Toni Janis Butan | CBG Granollers Keizars

## Slide 9: Result Quality Management ORGANIZATION TIMELINE PLAN MEETINGS
TOPICS | How
Objectives and results achieved during learning activities at the end of the final period of the project | Interview with Mr. Oliver Schneider Compare the responses of 2017 with those of 2018 Discussion with the referent of PractiGo (Miss Kerstin Hollwedel) Analyze proposed improvements right away, bringing a needs analysis within the meetings Murcia (Spain)
Proposals for improvement | Mr. Jan Lipke Project DECA local project manager (until December 2016) Mr. Nils Ruttmann Project DECA local project manager / VET Provider Tutor
Evaluation Companies | Interview with the Director of Haven Hostel Mr. Klaus Kentsch Interview with Pier6 Company’s Director Mr. Heumann
DECA management Evaluation, analysis of improvements proposals | Interview with Project Coordinator Dr. Uli Mix
Evaluation Students/ athletes | Interviews and questionnaires Compare the responses of 2017 with those of 2018

## Slide 10: Result Quality Management ORGANIZATION TIMELINE PLAN MEETINGS
TOPICS | How
Cooperation with Companies | Interview with Pier6 Company’s Director Mr. Heumann
DECA management Evaluation, analysis of improvements proposals | Interview with Project Coordinator Dr. Uli Mix Analyze improvements and advance proposals for improvement Compare the responses of 2017 with those of 2018
Evaluation Students/ athletes | Frontal interviews and questionnaires (personal description of their experience done until now, best practices, bad/good approach, etc.) Compare the responses of 2017 with those of 2018
Partners sport clubs 2018 | Cognitive survey based for the Sport Club who initially had a fundamental role (Try Outs) in the DECA project with a constant and reciprocal indirect involvement, representing the only remaining athletes Compare the responses of 2017 with those of 2018

## Slide 11
"Do not ask yourself what your teammates can do for you. Ask yourself what you can do for your teammates.
Earvin "Magic" Johnson, 1992.

## Slide 12
Thank you for your attention!!!
Mr. Spartaco Grieco
DECA Quality Manager
MSV Basket
Italy